## Bug_Tracking_Report
Bug Tracking Report
Project Name | Goa Credit Society
Product Owner | Himanshu Roy
Project Manager | Kavita Upadhye
Defect No. | Created Date | Created By | Defect Description | Priority | Assigned Date | Assigned to | Status
1 | 2022-01-24 | Priya K. | In Login module Password is not taking as per the requirement. | High | 2022-01-24 | Pranav Sharma | Close
2 | 2022-01-28 | John Leo | Not able to update members details in member module. | Medium | 2022-01-29 | Pranav Sharma | Open
3 | 2022-02-09 | Manan Pujari | Delete button is not working. | Medium | 2022-02-09 | Pranav Sharma | Open
4 | 2022-02-23 | Shreya Ghoshal | Not able to fill share details in share module | Low | 2022-02-25 | Pranav Sharma | Open
5 | 2022-03-03 | Sadhana S. | There is Spelling mistake in company name on home page | High | 2022-03-03 | Pranav Sharma | Close